**ACTION PLAN**

**A.Y. 2023-2024**

**GOOGLE DEVELOPER STUDENT CLUBS - HOLY NAME UNIVERSITY**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **SPECIFIC ACTIVITIES** | **OBJECTIVES** | **TARGET IMPACT** | **TIME FRAME** | | **RESOURCES NEEDED** | **PERSON/OFFICE RESPONSIBLE** |
| **START** | **END** |
| GDSC Info Session | To provide all members with a clear understanding of GDSC's essence and purpose. | The target impact of this goal is to ensure that all members gain a comprehensive comprehension of GDSC's core essence and its overarching purpose. | September 16, 2023 | September 16, 2023 | AV hall, or in the case of a larger number of participants, a gymnasium. | Organizational Officers |
| Engagement Activity | Virtual meeting with members. | The purpose of GDSC engagement activities is to foster active participation, interaction, and collaboration among members, enhancing their learning, networking, and overall experience within the community. | September 23, 2023 | September 24, 2023 | Online | Organizational Officers |
| General Meeting | To plan for events, delegate tasks and enhance team synergy. | Contributes higher rate of success on conducting future activities. | October 6, 2023 | October 6, 2023 | Room | Organizational Officers |
| Zuitt Partnership | Let interested people learn about HTML, CSS and Boot Strap. | The target impact of the GDSC X Zuitt partnership is to mutually enhance the learning opportunities and resources available to members, empowering them to acquire valuable tech skills and knowledge while furthering their career prospects. | October 7, 2023 | October 7, 2023 | Online | Organizational Officers |
| General Meeting | To plan for events, delegate tasks and enhance team synergy. | Contributes higher rate of success on conducting future activities. | October 27, 2023 | October 27, 2023 | Room | Organizational Officers |
| Project Management Software | Let GDSC members learn about project management and the software needed to implement it effectively and efficiently | empower GDSC members with comprehensive knowledge and skills in project management, equipping them with the necessary software tools and expertise to execute projects effectively and efficiently. | November 11, 2023 | November 11, 2023 | Scanlon Computer Laboratory | Maintenance, Ma’am Ligason |
| General Meeting | To plan for events, delegate tasks and enhance team synergy. | Contributes higher rate of success on conducting future activities. | October 27, 2023 | October 27, 2023 | Room | Organizational Officers |
| Hackathon | Encourage students to healthily compete and display their skills. | Strengthen the university’s future programmers. | November 11, 2023 | November 12, 2023 | Computer Laboratories / Online |  |
| Flutter workshop | The objectives of the Flutter workshop are multifaceted. First and foremost, it aims to introduce participants to the world of Flutter, elucidating its features and significance within the realm of mobile app development. | seeks to enhance the technical skills of participants, providing them with practical proficiency in Flutter app development and the confidence to create applications independently. | November 28, 2023 | November 28, 2023 | Scanlon Computer Laboratory | Organizational Officers |
| Engagement Activity | Virtual meeting with members. | The purpose of GDSC engagement activities is to foster active participation, interaction, and collaboration among members, enhancing their learning, networking, and overall experience within the community. | December 2, 2023 | December 2, 2023 | Online | Organizational Officers |
| Firebase workshop | aims to acquaint participants with Firebase, offering an understanding of its key features and capabilities. | equip participants with practical Firebase skills, enabling them to develop applications with real-time features and secure authentication | December 9, 2023 | December 9, 2023 | Scanlon Computer Laboratory | Organizational Officers |
| General Meeting | To plan for events, delegate tasks and enhance team synergy. | Contributes higher rate of success on conducting future activities. | October 27, 2023 | October 27, 2023 | Room | Organizational Officers |
| Solution Challenge Orientation | introduce participants to the competition's framework, guidelines, and expectations | equip participants with a comprehensive understanding of the competition's structure and requirements. It seeks to inspire them to think innovatively and collaboratively as they embark on the competition journey. | December 16, 2023 | December 16, 2023 | Scanlon Computer Laboratory | Organizational Officers |
| Generative AI workshop | provide participants with a foundational understanding of generative artificial intelligence, its principles, and its applications | provide participants with a foundational understanding of generative artificial intelligence, its principles, and its applications | January 14, 2023 | January 14, 2023 | Scanlon Computer Laboratory | Organizational Officers |
| Quiz Bowl | Active recall of every event | Embed participants with the knowledge learned | January 15, 2023 | January 15, 2023 | Online | Organizational Officers |